Logo, company name

Description automatically generated

Weekly Meeting Minutes

Date: February/03/2023

**ATTENDEES**

**Group-9 members present:**

* Kamaljit kaur (0792864)
* Krishnaben Gami (0790003)
* Prachi Vora: (0789897)
* Sukhjeet Kaur (0774458)
* Yashkumar Patel ( 0794142)

**Specific Activities that were completed/worked on:**

**Dataset Assessment:**

* **Sukhjeet kaur** & **Krishnaben Gami :**
* Worked on **Data pre-processing** using python. In this process we were exploring data by extracting images for project work, identifying issues, and removing them in order to make data consistent, and removing outliers, a set of images of the same dimension for using further model creation and training to have the same dimension. **(DONE)**

* **Prachi Vora/Yashkumar Patel/Kamaljit Kaur:**are working on **ethical Assessments** for data collection and usage along with EDA. Here, we are mainly focusing on data assessment revealing the images and exploring the dataset images dimensions by visualization and trying to find out the meaning from our data for train models for further prediction of breast cancer. (**IN PROGRESS)**

**Specific output from work:**

* As a team, we imported the dataset from Kaggle, and we all worked together on the first step of data assessment which is data - preprocessing and our dataset image consistent for further exploratory data Analysis.

**ON TARGET**

* **Green: everything is on track for completion by the due date**

**CHALLENGES/DISAGREEMENT**

* List any challenges identified/discussed and possible solutions.

We try to import our dataset into our internal storage of personal devices, but it takes too much during downloading then we extract directly data in the drive (Google collaborate) from Kaggle.

* List any notable disagreements and subsequent discussion and resolution.

Presently there are no notable disagreements.

**PLANNED ACTIVITIES FOR COMING WEEK**

|  |  |  |
| --- | --- | --- |
| **TASKS** | **ASSIGNED TO** | **ETA** |
| EDA | **Krishnaben Gami / Prachi Vora/ Sukhjeet Kaur / Kamaljit Kaur/ Yash Patel** | End of this week |
|  |  |  |
|  |  |  |